## Product_Backlog
Project Name | Freshworks CRM(Finanace)
Client | CRM
Created By | Group - 1 Team
Creation Date | 2023-04-05
Approval Date
Epic | User_Story_ID | Feature | User Story | Status | Acceptance Criteria
| US_001 | Validation of Searc products and filtering by different categories | User is able to search the product and apply filter on the Product. | Completed | 1. User should be able to search for the product and should provide the validated result. 2. User should be able to apply the filter on the search product. 3. Once the Filter is Applied search results should get modified Accordingly.
1 | US_002 | Validation of Global search dropdown | User is able to check the global search dropdown should get auto-selected when clicking on Electronics or Mobile or Fashions or Home and Kitchen or Books or Computers. By default it should be all even if we click on other option of the menu or invalid search in that category | Completed | 1. By default value of the dropdown should be All. 2. User select any of the listed value then the global search dropdown value should change Automatically. 3.If the user select electronic and search for shirt it should default to all because of invalid category.
| US_003 | Validation of Language dropdown functionality. | User should be able to change the language. | Completed | 1. On Mouse hover on EN user should be able to available languages like hindi, Marathi, English. 2. English should be defaulting language. 3. User should be able to see learn more button as a hyperlink and once click it should navigate to other page help and customer service. 4. User should be able to see the Country and Region hyperlink and, once clicked, should navigate to the website to select the country from a dropdown. 5. When the user clicks the en button, it should navigate to the language setting page.
| US_004 | Validation of Country selection flow | As per the Country selection Language and Url are changing and also verify value is appearing correct as per the translation. | Completed | 1. User selects the country example as China and then clicks on go. to website button. It should navigate to the correct page. 2. User should be able to see the language of the same country. 3. User should be able to see the local language option as per the country. 4. Local language list should appear correctly. 5. All the languages in the dropdown need to be checked.

## Sprint_Planning
Project Name | Amazon
Client | Public
Created By | Group - 1 Team
Attendees | Sunitha Padhi, Mahesh Bhapkar, Pooja Kambali, Jyoti Kushwaha
Creation Date | 2023-04-11
Epic | User_Story_ID | Feature | User Story | Sprint | Attendees
| US_001 | Validation of Searc products and filtering by different categories | User is able to search the product and apply filter on the Product. | 1 | Sunitha Padhi
1 | US_002 | Validation of Global search dropdown | User is able to check the global search dropdown should get auto-selected when clicking on Electronics or Mobile or Fashions or Home and Kitchen or Books or Computers. By default it should be all even if we click on other option of the menu or invalid search in that category | 1 | Mahesh Bhapkar
| US_003 | Validation of Language dropdown functionality. | User should be able to change the language. | 1 | Pooja Kambali
| US_004 | Validation of Country selection flow | As per the Country selection Language and Url are changing and also verify value is appearing correct as per the translation. | 1 | Jyoti Kushwaha
Story Points | Hours
1 | 1 Day
0, 1, 1, 2, 3, 5, 8 | Fibonacci Series

## Test_Scenario
Project Name |  | Amazon Shopping Website
Module Name |  | Amazon home page
Requirement Number |  | NA
Test case Type |  | Functionality Testing
Reference Document |  | NA
Pre-condition |  | User should create an account in Amazon
Test Data |  | https://www.freshworks.com/
Test_Scenario_No | User_Story_No | Description
User_Story_001: Sunitha Padhi
TS_001 | US_001 | To validate the functionality of the Search button.
TS_002 | US_001 | To validate the functionality of applying a filter on search results.
User_ Story_002: Maheshb Bhapkar
TS_003 | US_002 | Validate the interface of default global search dropdown.
TS_004 | US_002 | Validate the functinality of global search dropdown by clicking on listed value.
TS_005 | US_002 | Validate the functinality of global search dropdown by searching invalid category.
User_Story_003: Pooja Kambali
TS_006 | US_003 | Validate the functionality of change the language 'EN' button.
User_Story_004: Jyoti Kushwaha
TS_007 | US_004 | To Validate Country Button
TS_008 | US_004 | To Validate Language

## Test_Cases
Test_Case_No | User_Story_No | Test_Scenario_No | Test_Case_Name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tester | Test Status | Test Creation Date | Test Execution Date
TC_001 | US_001 | TS_001 | Search button Validation | Validate with valid desired product name in mobiles stream. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter a valid product name. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product : Samsung Mobile | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should be accepted and visible. Step 5: Should land on the Results page regarding the product. | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Landed on the Results page regarding the product and on the top diaplayed as "1-16 of 451 results for "samsung mobile" ". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_002 | US_001 | TS_001 | Search button Validation | Validate with valid desired product name in books stream. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter a valid product name. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: Harry Potter book sets | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should be accepted and visible. Step 5: Should land on the Results page regarding the product. | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Landed on the Results page regarding the product and on the top displayed as " 1-16 of over 2,000 results for "harry potter books set" ". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_003 | US_001 | TS_001 | Search button Validation | Validate with invalid data (INTEGER Data type with maximum limit) in the Search field. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter an invalid product name. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: 11111111111111111111111111111111111111111111111111111 | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should be accepted and visible. Step 5: Error should be displayed as "No results for 1111111111111111111111111111111111111111111111111111111111. Try checking your spelling or use more general terms". | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Did not land on the Results page and displayed an error message as "No results for 1111111111111111111111111111111111111111111111111111111111. Try checking your spelling or use more general terms". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_004 | US_001 | TS_001 | Search button Validation | Validate with invalid data (including both Integers and alphabetss) in the Search field. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter an invalid product name. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: 123samsung432 | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should be accepted and visible. Step 5: Error should be displayed as "No results for 123samsung432. Try checking your spelling or use more general terms". | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Did not land on the Results page and displayed an error message as "No results for 123samsung432. Try checking your spelling or use more general terms". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_005 | US_001 | TS_001 | Search button Validation | Validate with invalid data (Special characters) in the Search field. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter an invalid product name. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: @@@@!!!!!!!!!!! | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should not be accepted and visible. Step 5: Error should be displayed as "No results for @@@@!!!!!!!!!!!. Try checking your spelling or use more general terms". | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Landed on some undesired Results page. | High | P1 | Sunitha Padhi | FAIL | 2023-04-10 | 2023-04-10
TC_006 | US_001 | TS_001 | Search button Validation | Validate with invalid data (entering Space bar key for multiple times) in the Search field. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter space bar key for multiple times or leave empty. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should not be accepted and visible. Step 5: Error should be displayed as "Search Field is left empty.". | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Landed on same home page. | Low | P2 | Sunitha Padhi | FAIL | 2023-04-10 | 2023-04-10
TC_007 | US_001 | TS_001 | Search button Validation | Validate with invalid data (entering meaningless word with repeated alphabets ) in the Search field. | Step 1: Enter the URL on the browser page. Step 2: Sign in to Amazon with your account. Step 3: Do the mouse hover and click in the Search field. Step 4: Enter an invalid data. Step 5: Click on the Search button. | URL = "https://www.amazon.com" Product: aaaabbbbbcccc | Step 1: Should land on the Amazon Login page. Step 2: Should land on the Amazon home page. Step 3: The cursor should appear in the Search Field and user is able to enter a product name. Step 4: Data should not be accepted and visible. Step 5: Error should be displayed as "No results for aaaabbbbcccc. Try checking your spelling or use more general terms". | Step 1: Landed on the Amazon Login page. Step 2: Landed on the Amazon home page. Step 3: The cursor appeared in the Search Field and user is abled to enter a product name. Step 4: Data is accepted and visible. Step 5: Landed on some undesired Results page. | High | P1 | Sunitha Padhi | FAIL | 2023-04-10 | 2023-04-10
TC_008 | US_001 | TS_002 | Validation of Filter Applying on Search Product Results | Validate with 'All Prime' check box of Delivery Filter | Step 1: Enter the desired product name in the Search Field. Step 2: Click on the Search button. Step 3: Do the mouse hover on the 'All Prime' check box of Delivery Filter | Product: samsung mobile | Step 1: Data should be accepted and visible. Step 2: Should land on the Results page regarding the product. Step 3: The check box should be highlighted with blue colour and 'All Prime' word's font color should change in to red colour. | Step 1: Data is accepted and visible. Step 2: Landed on the Results page regarding the product and on the top diaplayed as "1-16 of 451 results for "samsung mobile" ". Step 3: The check box is highlighted with blue colour and 'All Prime' word's font color changed in to red colour. | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC-009 | US_001 | TS_002 | Validation of Filter Applying on Search Product Results | Validate with 'Get it by Tomorrow' check box of Delivery Day Filter | Step 1: Enter the desired product name in the Search Field. Step 2: Click on the Search button. Step 3: Do the mouse hover on the 'Get it by Tomorrow' check box of Delivery Day Filter | Product: samsung mobile | Step 1: Data should be accepted and visible. Step 2: Should land on the Results page regarding the product. Step 3: The check box should be highlighted with blue colour and 'Get it by Tomorrow' word's font color should change in to red colour. | Step 1: Data is accepted and visible. Step 2: Landed on the Results page regarding the product and on the top diaplayed as "1-16 of 451 results for "samsung mobile" ". Step 3: The check box is highlighted with blue colour and 'Get it by Tomorrow' word's font color changed in to red colour. | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_010 | US_001 | TS_002 | Validation of Filter Applying on Search Product Results | Validate with 'Children's Fantasy, Science Fiction & Horror' option of Books of Category Filter | Step 1: Enter the desired product name in the Search Field. Step 2: Click on the Search button. Step 3: Do the mouse hover on the 'Children's Fantasy, Science Fiction & Horror' option of Books of Category Filter. | Product: Harry Potter book sets | Step 1: Data should be accepted and visible. Step 2: Should land on the Results page regarding the product. Step 3: The selected option 'Children's Fantasy, Science Fiction & Horror' word's font color should change in to red colour. | Step 1: Data is accepted and visible. Step 2: Landed on the Results page regarding the product and on the top displayed as "1-16 of over 2,000 results for "harry potter books set" ". Step 3: The selected option 'Children's Fantasy, Science Fiction & Horror' word's font color changed in to red colour. | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_011 | US_001 | TS_002 | Validation of Filter Apply on Search Product Results functionality | Validate with 'All Prime' check box of Delivery Filter | Step 1: Enter the desired product name in the Search Field. Step 2: Click on the Search button. Step 3: Do the mouse hover on the 'All Prime' check box of Delivery Filter. Step 4:Click on the check box. | NA | Step 1: Data should be accepted and visible. Step 2: Should land on the Results page regarding the product. Step 3: The check box should be highlighted with blue colour and 'All Prime' word's font color should change in to red colour. Step 4: Should land on the new Results page with respect to the selected option of the applied filter. | Step 1: Data is accepted and visible. Step 2: Landed on the Results page regarding the product and on the top diaplayed as "1-16 of 451 results for "samsung mobile" ". Step 3: The check box is highlighted with blue colour and 'All Prime' word's font color changed in to red colour. Step 4: Landed on the new Results page with respect to the selected option of the applied filter and on the top diaplayed as "1-16 of 387 results for "samsung mobile" ". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TC_012 | US_001 | TS_002 | Validation of Filter Apply on Search Product Results functionality | Validate with 'All Prime' check box of Delivery Filter, Samsung check box of Brands Filter, ₹1,000 - ₹5,000 of Price filter. | Step 1: Enter the desired product name in the Search Field. Step 2: Click on the Search button. Step 3: Do the mouse hover on the 'All Prime' check box of Delivery Filter. Step 4: Click on the All Prime check box. Step 5: Do the mouse hover on the 'Samsung' check box of Brands Filter. Step 6: Click on the Samsung check box. Step 7: Do the mouse hover on the ₹1,000 - ₹5,000 option of Price filter. Step 8: Click on the ₹1,000 - ₹5,000 option. | NA | Step 1: Data should be accepted and visible. Step 2: Should land on the Results page regarding the product. Step 3: The check box should be highlighted with blue colour and 'All Prime' word's font color should change in to red colour. Step 4: Should land on the new Results page with respect to the selected option of the applied filter. Step 5: The check box should be highlighted with blue colour and 'Samsung' word's font color should change in to red colour. Step 6: Should land on the new Results page with respect to the selected option of the applied filter. Step 7: '₹1,000 - ₹5,000 ' font color should change in to red colour. Step 8: Should land on the new Results page with respect to the selected option of the applied filter. | Step 1: Data is accepted and visible. Step 2: Landed on the Results page regarding the product and on the top diaplayed as "1-16 of 451 results for "samsung mobile" ". Step 3: The check box is highlighted with blue colour and 'All Prime' word's font color changed in to red colour. Step 4: Landed on the new Results page with respect to the selected option of the applied filter and on the top diaplayed as "1-16 of 387 results for "samsung mobile" ". Step 5: The check box is highlighted with blue colour and 'Samsung' word's font color changed in to red colour. Step 6: Landed on the new Results page with respect to the selected option of the applied filter and on the top diaplayed as "1-16 of 323 results for "samsung mobile" ". Step 7: '₹1,000 - ₹5,000 ' font color changed in to red colour. Step 8: Landed on the new Results page with respect to the selected option of the applied filter and on the top diaplayed as "23 results for "samsung mobile"". | NA | NA | Sunitha Padhi | PASS | 2023-04-10 | 2023-04-10
TESTER : Mahesh Bhapkar
TC_013 | US_002 | TS_003 | Validate the interface of default global search dropdown | Validate the interface of default global search dropdown | 1. Open the Website https://www.amazon.in/ 2. Check the global search dropdown interface. 3. Click on the global search dropdown. 4. Scroll down in global search dropdown. 5. Scroll up in global search dropdown | NA | 1. Should land on https://www.amazon.in/ 2. By default global search dropdown value should be "All" 3. Global search dropdown should be clickable & should display the different categories listed by ascending order, dropdown should be highlighted in orange border. 4. User should be able to scroll down in global search dropdown. 5.User should be able to scroll up in global search dropdown | 1. Landed on https://www.amazon.in/ 2. By default global search dropdown value was"All" 3. Global search dropdown was clickable & displayed the different categories listed by ascending order, dropdown was highlighted in orange border. 4. User able to scroll down in global search dropdown. 5.User able to scroll up in global search dropdown. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_014 | US_002 | TS_003 | Validate the interface of default global search dropdown | Validate the interface of default global search dropdown by clicking on other options of menu | 1. Open the Website https://www.amazon.in/ 2. Check the global search dropdown interface. 3. Click on select your address option in the top menu. | NA | 1. Should land on https://www.amazon.in/ 2. By default global search dropdown value should be "All" 3. Global search dropdown value should not be changed. | 1. Landed on https://www.amazon.in/ 2. By default global search dropdown value was"All" 3. Global search dropdown value did not changed. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_015 | US_002 | TS_003 | Validate the interface of default global search dropdown | Validate the interface of default global search dropdown by doing invalid search | 1. Open the Website https://www.amazon.in/ 2. Check the global search dropdown interface. 3. Type the invalid product in the search bar. 4. Click on search button. | Product to search : hujirdhsj | 1. Should land on https://www.amazon.in/ 2. By default global search dropdown value should be "All". 3. User should be able to type in the Search bar & typed text should visible. 4. Button should be clickable & global search dropdown value should be "All". | 1. Landed on https://www.amazon.in/ 2. By default global search dropdown value was"All" 3. User able to type in the Search bar & typed text was visible. 4. Button was clickable & global search dropdown value was "All". | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_016 | US_002 | TS_003 | Validate the interface of default global search dropdown | Validate the interface of default global search dropdown on small laptop screens | 1. Open the Website https://www.amazon.in/ on small laptop screens. 2. Check the global search dropdown interface. | NA | 1. Should land on https://www.amazon.in/ 2. By default global search dropdown value should be "All" & menu items Electronics, Mobile,Fashions,Home and kitchen,Books ,Computers should be displayed. | 1. Landed on https://www.amazon.in/ 2. By default global search dropdown value was"All" but menu items Fashions,Home and kitchen,Books ,Computers was not displayed. | Medium | High | Mahesh Bhapkar | FAIL | 2023-04-10 | 2023-04-11
TC_017 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Electronics | 1. Open the Website https://www.amazon.in/ 2. Click on Electonics option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Electronics | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Electronics". 3. Should only display the electroncis items on the page. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Electronics". 3. Only displayed the electroncis items on the page. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_018 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Mobile | 1. Open the Website https://www.amazon.in/ 2. Click on Mobile option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Mobile | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Mobiles & accessories". 3. Should only display the all types of mobiles items on the page. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Mobiles & accessories". 3. Only displayed the mobile items on the page. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_019 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Fashions | 1. Open the Website https://www.amazon.in/ 2. Click on Fashions option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Fashions | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Amazon Fashion". 3. Should display only the clothing items on the page. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Amazon Fashion". 3. Only displayed the fashion items on the page. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_020 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Home and Kitchen | 1. Open the Website https://www.amazon.in/ 2. Click on Home & Kitchen option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Home & kitchen | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Home & Kitchen". 3. Should display only the home & kitchen items on the page. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Home & Kitchen". 3. Only displayed the Home & Kitchen items on the page. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_021 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Books | 1. Open the Website https://www.amazon.in/ 2. Click on Books option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Books | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Books". 3. Should display only the book related items on the page. | 1. Landed on https://www.amazon.in/ 2. Books option is not displayed on the webpage. 3. Book related items not displayed | Medium | High | Mahesh Bhapkar | FAIL | 2023-04-10 | 2023-04-11
TC_022 | US_002 | TS_004 | Validate the functinality of global search dropdown by clicking on listed value | Validate the functinality of global search dropdown by clicking on Computers | 1. Open the Website https://www.amazon.in/ 2. Click on Computers option in the menu. 3. Validate the interface of global search dropdown | Selection of option : Computers | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Computers & accessories". 3. Should display only the computer & its accessories items on the page. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Computers & accessories". 3. Only displayed the Computers & accessories items on the page. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TC_023 | US_002 | TS_005 | Validate the functinality of global search dropdown by searching invalid category | Validate the functinality of global search dropdown by searching invalid category | 1. Open the Website https://www.amazon.in/ 2. Click on Electonics option in the menu. 3. Validate the interface of global search dropdown. 4. Type the text "shirt" in the search bar. 5. Click on search button 6. Validate the interface of global search dropdown | Search text : "shirt" | 1. Should land on https://www.amazon.in/ 2. Global search dropdown option should automatically select the "Electronics". 3. Should only display the electroncis items on the page. 4. Search bar should be highlited in the orange border & typed text should be visible. 5. Button should be clickable. 6. Global search dropdown should change to the all because of invalid catergory & should display the shirt items. | 1. Landed on https://www.amazon.in/ 2. Global search dropdown option automatically selected the "Electronics". 3. Displayed only the electroncis items on the page. 4. Search bar were highlited in the orange border & typed text was visible. 5. Button was clickable. 6. Global search dropdown changed to the all because of invalid catergory & displayed the shirt items. | NA | NA | Mahesh Bhapkar | PASS | 2023-04-10 | 2023-04-11
TESTER : Pooja Kambali
TC_024 | US_003 | TS_006 | Validate users are able to see 'EN button along with country flag logo is display on the top right side. | User want to check weather change the language button 'EN' and country flag logo are display | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag are display present at the top sight side. | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_025 | US_003 | TS_006 | Validate the functionality of 'EN' button | User want to check language like hindi, marathi, hindi etc. are avaliable after mouse hovering on 'EN' button. | Step1: Enter the URL. Step2: Check 'EN button is display at the top right side. Step3: mouse hover on 'EN' button and check lanuage like hindi, marathi, english etc. and some other options are avaliable | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: should be able to mouse hover on 'EN' button and able to see language like hindi, marathi, english etc. and some other options are visible | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag are display present at the top sight side. Step3: Was able to mouse hover on 'EN' button and able to see language like hindi, marathi, english etc. and some other options are visible | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_026 | US_003 | TS_006 | Validate the functionality of change current language | User want to change language as Hindi | Step1: Enter the URL. Step2: Check 'EN button is display at the top right side. Step3: mouse hover on 'EN' button and clilck on Hindi radio button Step4: Check Hindi is set as a current language | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: Should be able to mouse hover on 'EN' button and clilck on Hindi radio button. Step4: Should be able to check Hindi is set as a current language. | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Was able to mouse hover on 'EN' button and clilck on Hindi radio button. Step4: Was able to check Hindi is set as a current language. | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_027 | US_003 | TS_006 | validate the functionality of the default language | User want to check English language is set as default language | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: mouse hover on 'EN' button and check english language is set as defaulting language | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: After mouse hovering on 'EN' button, user should be able to see english language is set as defaulting language. | Step1: Wasable to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: After mouse hovering on 'EN' button, user was able to see english language is set as defaulting language. | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_028 | US_003 | TS_006 | Validate the functionality of 'elearn more' hyperlink | User want to see learn more button is in a hyperlink form | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: Mouse hover on 'EN' button and see learn more button is in a hyperlink form | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: User should be able to mouse hover on EN button and see learn more button is in a hyperlink form. | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on EN button and user should be able to see learn more button as a hyperlink and once click it should navigate to other page help and customer service | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_029 | US_003 | TS_006 | Validate the functionality of 'learn more' hyperlink | User want to see once click on learn more button should navigate to other page help and customer service | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: Mouse hover on 'EN' button and check once click on learn more button it should navigate to other page help and customer service | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user should be able to check once click on learn more button it should navigate to other page help and customer service | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user was able to see learn more button as a hyperlink and once click it should navigate to other page help and customer service | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_030 | US_003 | TS_006 | Validate the functionality of ' country and region' hyperlink | User want to see country and region hyperlink | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: Mouse hover on 'EN' button and see country and region is in a hyperlink form | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user should be able to see country and region button is in hyperlink form | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user was able to see country and region button is in hyperlink form | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_031 | US_003 | TS_006 | Validate the functionality of ' country and region' hyperlink | User want to check once click on country and region hyperlink should navigate to website to select country from dropdown | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: Mouse hover on 'EN' button and check once click on country and region hyperlink it should navigate to website to select country from dropdown | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user should be able to check once click on country and region button it should navigate to website to select country from a dropdown. | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Mouse hover on 'EN' button and user was able to check once click on country and region button it should navigate to website to select country from a dropdown. | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
TC_032 | US_003 | TS_006 | Validate the functionality of 'EN' button | User want to check when click on 'EN' button it should navigate to language setting page | Step1: Enter the URL. Step2: Check 'EN button and country flag logo are display at the top right side. Step3: Click on 'EN' button and check it should navigate to language setting page | URL : www.amazon.in | Step1: User Should be able to land on home page. Step2: Should be able to see 'EN' button and country flag present at the top sight side. Step3: User should be able to click on 'EN' button and check it should navigate to language setting page | Step1: Was able to land on home page. Step2: Was able to see 'EN' button and country flag present at the top sight side. Step3: Was able to click on 'EN' button and check it should navigate to language setting page | NA | NA | Pooja Kambali | PASS | 2023-04-10 | 2023-04-10
Tester: Jyoti Kushwaha
TC_033 | US_004 | TS_007 | Country Button Validation | Launch the Application | Launch the application as per provided URL | https://www.amazon.in/ | Application should launch successfully | Application launched successfully | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_034 | US_004 | TS_007 | Country Button Validation | Validate the Brazil Countries Buttons Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3.Select the Brazil Country Button. 4.Navigated to the Selected Country page. 5.Back to previous page. | NA | After clicking Country Button it should enable and clickable Should Navigate to the Selected Country page | After clicking Country Button it is enable and clickable Navigated to Selected Country page | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_035 | US_004 | TS_007 | Country Button Validation | Validate the Australia Country Button Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3.Select the Australia Country Button. 4.Navigated to the Selected Country page. 5.Back to previous page. | NA | After clicking Country Button it should enable and clickable Should Navigate to the Selected Country page | After clicking Country Button it is enable and clickable Navigated to Selected Country page | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_036 | US_004 | TS_007 | Country Button Validation | Validate the Canada Country Button Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3. Select the Canada Country Button. 4.Navigated to the Selected Country page. 5.Back to previous page. | NA | After clicking Country Button it should enable and clickable Should Navigate to the Selected Country page | After clicking Country Button it is enable and clickable Navigated to Selected Country page | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_037 | US_004 | TS_007 | Country Button Validation | Validate the Spain Country Button Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3.Select the Spain Country Button. 4.Navigated to the Selected Country page. 5.Back to previous page. | NA | After clicking Country Button it should enable and clickable Should Navigate to the Selected Country page | After clicking Country Button it is enable and clickable Navigated to Selected Country page | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_038 | US_004 | TS_007 | Country Button Validation | Validate the Canada Country Button in Canada Amazon Page Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3.Select the Canada Country Button. 4.Navigated to the Selected Country page 5.Scroll Down the Page Select Any Country Option | NA | After scrolling Down Canada Amazon Country Page Countries Button should be Visbile and Enable at the Bottom of the Page | After scrolling Down Canada Amazon Country Page Countries Button is not Visbile and Enable at the Bottom of the Page | High | P2 | Jyoti Kushwaha | FAIL | 2023-04-10 | 2023-04-11
TC_039 | US_004 | TS_008 | Language Validation | Validate the Spain Country language button Dispaying Button Functionality | 1.Landed to Home Page. 2.Scroll drawn the screen. 3.Select the Spain Country Button. 4.Navigated to the Selected Country page. 5.At Top Right Click Langauage Button | NA | At Click Top Right Local Langauage Button should enable and clickable | At Click Top Right Local Langauage Button is enable and clickable | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_040 | US_004 | TS_008 | Language Validation | Validate Language Button Dropdown Functionality | 1.Click to Spain Country Language Dropdown Button | NA | Button should be enable and clickable | Buuton is be enable and clickable | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_041 | US_004 | TS_008 | Language Validation | Validate Language Button Dropdown list Functionality | 1.Click to Spain Country Language Dropdown Button | NA | Spain Country Language Dropdown List Button should be enable and visible while the List Appear español - ES And português - PT langauge should visible and enable | Spain Country Language Dropdown List Button is be enable and visible while the List Appear español - ES And português - PT langauge is visible and enable | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_042 | US_004 | TS_008 | Language Validation | Validate Default Langauage | 1.Click to Spain Countary Dropdown Button | NA | By Default português - PT langauge should visible and enable | By Default português - PT langauge is visible and enable | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_043 | US_004 | TS_008 | Language Validation | Validate español - ES Langauage | 1.Click to Spain Countary Dropdown 2.Click to español - ES Langauage | NA | español - ES Language should be enable and clickable. Page language converted into español - ES Langauage | español - ES Language should be enable and clickable.Page language converted into español - ES Langauage | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_044 | US_004 | TS_008 | Language Validation | Validate português - PT Langauage | 1.Click to Spain Countary Dropdown 2.Click to português - PT Langauage | NA | português - PT Language should be enable and clickable. Page language converted into português - PT Langauage | PT Langauage Language should be enable and clickable.Page language converted into español - PT Langauage | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_045 | US_004 | TS_008 | Language Validation | Validate Language Setting Functionality | 1.Double to Spain Language Button | NA | Language setting option should appear and all option should be enable and clickable | Language setting option is appeared and all option is enable and clickable | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11
TC_046 | US_004 | TS_008 | Language Validation | Validate Language Setting options Functionality | 1.Double to Spain Language Button | NA | español - ES and português - PT - Tradução options should enable with radio buttons | español - ES and português - PT - Tradução options is enable with radio buttons | NA | NA | Jyoti Kushwaha | PASS | 2023-04-10 | 2023-04-11

## Test_Execution_Details
Test_Case_No | Test_Case_Name | Snapshots
TC_001 | Search button Validation
TC_002 | Search button Validation
TC_003 | Search button Validation
TC_004 | Search button Validation
TC_005 | Search button Validation
TC_006 | Search button Validation
TC_007 | Search button Validation
TC_008 | Validation of Filter Applying on Search Product Results
TC_009 | Validation of Filter Applying on Search Product Results
TC_010 | Validation of Filter Applying on Search Product Results
TC_011 | Validation of Filter Apply on Search Product Results functionality
TC_012 | Validation of Filter Apply on Search Product Results functionality
Tester: Mahesh Bhapkar
TC_013 | Validate the interface of default global search dropdown
TC_014 | Validate the interface of default global search dropdown
TC_015 | Validate the interface of default global search dropdown
TC_016 | Validate the interface of default global search dropdown
TC_017 | Validate the functinality of global search dropdown by clicking on listed value
TC_018 | Validate the functinality of global search dropdown by clicking on listed value
TC_019 | Validate the functinality of global search dropdown by clicking on listed value
TC_020 | Validate the functinality of global search dropdown by clicking on listed value
TC_021 | Validate the functinality of global search dropdown by clicking on listed value
TC_022 | Validate the functinality of global search dropdown by clicking on listed value
TC_023 | Validate the functinality of global search dropdown by searching invalid category
TESTER:Pooja Kambali
TC_024 | Validate users are able to see 'EN button along with country flag logo is display on the top right side.
TC_025 | Validate the functionality of 'EN' button
TC_026 | Validate the functionality of change current language
TC_027 | validate the functionality of the default language
TC_028 | Validate the functionality of 'elearn more' hyperlink
TC_029 | Validate the functionality of 'learn more' hyperlink
TC_030 | Validate the functionality of ' country and region' hyperlink
TC_031 | Validate the functionality of ' country and region' hyperlink
TC_032 | Validate the functionality of 'EN' button
Tester: Jyoti Kushwaha
TC_033 | Countary Button Validation
TC_034 | Countary Button Validation
TC_035 | Countary Button Validation
TC_036 | Countary Button Validation
TC_037 | Countary Button Validation
TC_038 | Countary Button Validation
TC_039 | Language Validation
TC_040 | Language Validation
TC_041 | Language Validation
TC_042 | Language Validation
TC_043 | Language Validation
TC_044 | Language Validation
TC_045 | Language Validation
TC_046 | Language Validation

## Defects
Defect_No | Project Name | Module Name | Requirement_No | Test_Case_No | Summary | Descriptiom | Issues | Severity | Priority | Assign to
DN_001 | Amazon Shoppiing | Amazon Home Page | User_Story_001 | TC_005 | Search button Validation | When the user enters invalid data like Special characters in the Search field and clicks on Search button, some Results page is landed.But it should display an erroe message as "No results for @@@@!!!!!!!!!!!. Try checking your spelling or use more general terms". | Landed on some undesired Results page when some special characters are entered in the Search field. | High | P1 | Sunitha Padhi
DN_002 | Amazon Shoppiing | Amazon Home Page | User_Story_001 | TC_006 | Search button Validation | When the user enter space bar key for multiple times or leave empty in the Search Field and clicks on the Search button, landed on the home page again. But it should display an error message as "Search Field is left empty.". | Landed on home page again when space bar key entered for multiple times in the Search field or when the Search Field left empty. | Low | P2 | Sunitha Padhi
DN_003 | Amazon Shoppiing | Amazon Home Page | User_Story_001 | TC_007 | Search button Validation | When the user enters invalid data like meaningless word with repeated alphabets in the Search Field and clicks on Search button, some Results page is landed.But it should display an erroe message as "No results for @@@@!!!!!!!!!!!. Try checking your spelling or use more general terms". | Landed on some undesired Results page when some meaning less word with repeated alphabets is entered in the Search field. | High | P1 | Sunitha Padhi
Tester: Mahesh Bhapkar
DN_004 | Amazon Shoppiing | Amazon Home Page | User_Story_002 | TC_016 | Validate the interface of default global search dropdown on small laptop screens | On the small laptop screens menu items Fashions,Home and kitchen,Books,Computers | On the small laptop screens menu items Fashions,Home and kitchen, Books, Computers | MEDIUM | P2 | Mahesh Bhapkar
DN_005 | Amazon Shoppiing | Amazon Home Page | User_Story_002 | TC_021 | Validate the functinality of global search dropdown by clicking on Books | Books option in the menu is not displayed | Books option in the menu is not displayed | MEDIUM | P1 | Mahesh Bhapkar
Tester : Jyoti Kushwaha
DN_006 | Amazon Shoppiing | Language Functionality | User_Story_004 | TC_038 | Language Selection Validation | Validate the Canada Countary Button in Canada Amazon Page Functionality | After scrolling Down Canada Amazon Country Page Countries Button is not be Visbile and Enable at the Bottom of the Page | HIGH | P2 | Jyoti Kushwaha

## Defect_Snapshots
Defect_No | Issues | Snapshots
DN_001 | Landed on some undesired Results page when some special characters are entered in the Search field.
DN_002 | Landed on home page again when space bar key entered for multiple times in the Search field or when the Search Field left empty.
DN_003 | Landed on some undesired Results page when some meaning less word with repeated alphabets is entered in the Search field.
Tester: Mahesh Bhapkar
DN_004 | On the small laptop screens menu items Fashions,Home and kitchen, Books, Computers
DN_005 | Books option in the menu is not displayed
Tester: Jyoti Kushwala
DN_006 | After scrolling Down Canada Amazon Country Page Countries Button is not be Visbile and Enable at the Bottom of the Page

## Story_Point_Effort_And_Reason
USER_STORY_001 :- | Sunitha Padhi
Project Name : | Amazon Shopping
Story Point: | 3
Reason for Story Point: | Complexity in searching by entering different possibilities in the Search Field and checking by applying different filters on the Search product Results page, doing more efforts in defect finding and also for the execution of each and every field in Search product Results module.
Efforts(in hours): | 6hrs/day
Reason for Efforts: | 3hrs for Test Design, 2hrs for Execution and 1hr for Defect Retesting.
USER_STORY_002:- | Mahesh Bhapkar
Project Name : | Amazon Shopping
Story Point: | 3
Reason for Story Point: | Complexity in validating the Global Search dropdown with different multiple options is medium and also for finding defects and retesting them.
Efforts(in hours): | 5hrs/day
Reason for Efforts: | 3hrs for Test Design, 1hr for Execution and 1hr for Defect Retesting.
USER_STORY_003:- | Pooja Kambali
Project Name : | Amazon Shopping
Story Point: | 3
Reason for Story Point: | Complexity to validate EN drop down and check for different languages and also for validating the country/region flow.efforts made for doing functionality testing for various fields.
Efforts(in hours): | 5hrs/day
Reason for Efforts: | 3hrs for Test Design, 2hrs for Execution
USER_STORY_004 | Jyoti Kushwaha
Project Name : | Amazon Shopping
Story Point: | 3
Reason for Story Point: | Complexity on understanding the acceptance criteria and in Validating Different Countries Buttons and Executing them, Validating the Local Language of the Spain Countary and efforts made for defect finding and retesting them.
Efforts(in hours): | 5hrs/day
Reason for Efforts: | 3hrs for Test Design, 1hr for Execution and 1hr for Defect Retesting.

## Test_Report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO(%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | 40 | 6 | 0 | 0 | 46 | 86.95% | 0 | 0 | 46 | 6