## Product_Backlog
Project Name | Freshworks CRM(Finanace)
Client | CRM
Created By | Group - 1 Team
Creation Date | 2023-04-05
Approval Date
Epic | User_Story_ID | Feature | User Story | Status | Acceptance Criteria
| US_001 | Add contact and Group by Validation | The user should be able to add a contact in My contacts list and able to edit and sort all the columns in the form of a Table or Kanban. | Completed | 1. My Contact tab user should be able to add the contact 2. User should be able to see the layover form for creating the contact. 3. User should be able to sort all the Columns in ascending and Descending order. 4. All the fields should have an edit icon and the user change the value Right away. 5. User is able to see the Drop of the table and Kanban so the UI will change accordingly. 6. User should be able to see Group by Button with Multiple Dropdown Option. 7. On selection of the Group by the Value Board should change according
1 | US_002 | Document Uploading | The user should be able to upload documents and able to select single or multiple documents. | Completed | 1. User should be able to see Document Tab with My Document. 2. User should be able to see the existing documents. 3. User should be to select Multiple Documents all Together. 4. User should be able to see the edit account on the grid. 5. ALL the Columns are Sortable.
| US_003 | Document Handling | The user should be able to see three buttons (Assign to, update Field and Delete) and able to update documents with respect to these buttons. | Completed | 1. Once select document user should be see 3 buttons at top (Assign to, update Field and Delete) 2. User should be able to assign a Document but once pop-up screen will appear with a message” Select sales owner” and 2 button save and cancel and text field. 3. Once Click on save it should get assigned and once click on Cancel it should navigate back to the parent page. 4. User should be able to update the field of the document but once a pop-up screen will appear with the message” Search for a field and update it” and 2 buttons save and Cancel and Dropdown fields. 5. Once Click on save it should get saved and appear in the grid and once click on Cancel it should navigate back to the parent page. The user should be able to delete the document but once a pop-up screen will appear with the message” 1 document will be deleted, along with all related activities. Clicking Yes deletes every document you have selected. If any of these documents are synced to deals, only the documents will be deleted; there will be no impact on the products you have added to the deals. Go ahead and delete?" 6. 2 buttons yes and no and a text field. 7. Once Click on yes it should get deleted and should not appear in the grid and once click on no it should navigate back to the parent page.
| US_004 | Add Product and Slecting Products | The user should be able to add products and able to select Single and multiple products. | Completed | 1. User should be able to see product tab 2. User should be able to add Product once added it should appear in the grid 3. User should be able to see the existing product 4. User should be to select Multiple product all Together. 5. User should be able to see edit account on the grid (except base amount and created date) 6. ALL the Columns are Sortable 7. It should how number of Record with page bottom of table “Showing 1 - 2 of 2”

## Sprint_Planning
Project Name | Freshworks CRM(Finance Domain)
Client | Freshworks CRM
Created By | Group - 1 Team
Attendees | Sunitha Padhi, Mahesh Bhapkar, Pooja Kambali, Jyoti Kushwaha
Creation Date | 2023-04-05
Epic | User_Story_ID | Feature | User Story | Sprint | Attendees
| US_001 | Add contact and Group by Validation | The user should be able to add a contact in My contacts list and able to edit and sort all the columns in the form of a Table or Kanban. | 1 | Sunitha Padhi
1 | US_002 | Document Uploading | The user should be able to upload documents and able to select single or multiple documents. | 1 | Mahesh Bhapkar
| US_003 | Document Handling | The user should be able to select a document and check the appearance of Assign to, Update Field, Delete buttons | 1 | Pooja Kambali
| US_004 | Add Product and Slecting Products | The user should be able to add products and able to select Single and multiple products. | 1 | Jyoti Kushwaha
Story Points | Hours
1 | 1 Day
0, 1, 1, 2, 3, 5, 8 | Fibonacci Series

## Test_Scenario
Project Name |  | Freshworks CRM(Finance Domain)
Module Name |  | Fresh works CRM
Requirement Number |  | NA
Test case Type |  | Functionality Testing
Reference Document |  | NA
Pre-condition |  | User should create an account in Freshworks
Test Data |  | https://www.freshworks.com/
Test_Scenario_No | User_Story_No | Description
TS_001 | US_001 | To validate the functionality of ' Add contact ' tab in CRM sales Freshworks page and validate sorting the list in ascending and descending order.
TS_002 | US_001 | To validate the functionality of ' Group by ' button in CRM sales Freshworks page.

## Test_Cases
Test_Case_No | User_Story_No | Test_Scenario_No | Test_Case_Name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tester | Test Status | Test Creation Date | Test Execution Date | Screen Shots
TC_001 | US_001 | TS_001 | Add contact tab validation | Validate with valid contact details. | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Enter valid first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter a valid email address and select any option in the Pick a Label. Step 7: Click on Add email button. Step 8: Enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Mamta Last name: Mohta email: mamta123@gmail.com mobile no:7000004444 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: Data should not be accepted and an error message should be displayed as selected and visible. Step 7: Email address should be acceptd and visible. Step 8: Data should be accepted and visible. Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: New contact should be added in the My contacts list. | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: Data is accepted and the option is selected and visible. Step 7: Email address is added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is added in the My contacts list. | High | P1 | Sunitha Padhi | PASS | 2023-04-01 | 2023-04-01
TC_002 | US_001 | TS_001 | Add contact tab validation | Validate with invalid email address. | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Enter valid first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an invalid email address and select any option in the Pick a Label. Step 7: DO not click on Add email button. Step 8: Enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Naveen Last name: Roy email: ssss.gmail.com mobile no:7000004545 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: Data should be accepted and the option should be selected and visible. Step 7: Email address should not be accepted and not visible. Step 8: Data should be accepted and visible. Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: An error message should be displayed under Emails as "Is invalid" and should not add the contact. | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: Data is accepted and the option is selected and visible. Step 7: Email address is added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is not added to the My contacts list and an error message is displayed as "Is invalid". | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_003 | US_001 | TS_001 | Add contact tab validation | Validate with blank email address. | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Enter valid first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Do not enter an email address and select any option in the Pick a Label. Step 7: Do not click on Add email button. Step 8: Enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Naveen Last name: Roy email: blank mobile no:7000004545 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: No data should be accepted and the Pick a Label option should be selected and visible. Step 7: Email address should not be accepted and not visible. Step 8: Data should be accepted and visible. Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: An error message should be displayed under Emails as "Need to fill this Emails to submit the form." and should not add the contact. | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: No data is accepted and the Pick a Label option is selected and visible. Step 7: Email address is not added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is not added to the My contacts list and an error message is displayed as "Need to fill this Emails to submit the form.". | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_004 | US_001 | TS_001 | Add contact tab validation | Validate with exist email address. | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Enter valid first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an email address which is already exist in the contact list and select any option in the Pick a Label. Step 7: Do not click on Add email button. Step 8: Enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Mamta Last name: Sathe email: mamta123@gmail.com mobile no:7894000000 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: No data should be accepted and the Pick a Label option should be selected and visible. Step 7: Email address should not be accepted and not visible. Step 8: Data should be accepted and visible. Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: An error message should be displayed as " Failed to create Contact. mamta123@gmail already exists." and should not add the contact. | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: No data is accepted and the Pick a Label option is selected and visible. Step 7: Email address is not added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is not added to the My contacts list and an error message is displayed as "Failed to create the Contact.mamta123@gmail.com already exists.". | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_005 | US_001 | TS_001 | Add contact tab validation | Validate with blank first name and last name. | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Do not enter any first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an email address and select any option in the Pick a Label. Step 7: Click on Add email button. Step 8: Enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Last name: email: larva123@gmail.com mobile no:7890000234 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: An error message should be displayed as "The field should not be left blank". Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: No data should be accepted and the Pick a Label option should be selected and visible. Step 7: Data should be accepted and visible. Step 8: Data should be accepted and visible. Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: An error message should be displayed as " The field should not be left blank." and should not add the contact. | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted. Step 5: The selected account is accepted and visible. Step 6: No data is accepted and the Pick a Label option is selected and visible. Step 7: The email address is not added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is added by email address. | High | P1 | Sunitha Padhi | FAIL | 2023-04-03 | 2023-04-03
TC_006 | US_001 | TS_001 | Add contact tab validation | Validate with invalid mobile number | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Do not enter any first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an email address and select any option in the Pick a Label. Step 7: Click on Add email button. Step 8: Enter an invalid mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Priya Last name: Mudrali email: priya@gmail.com mobile no:00000000000 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: Data should not be accepted and an error message should be displayed as "The field should not be left blank.". Step 7: The email address should be accepted and visible. Step 8: Should display an error message as "Invalid mobile number." Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: New contact should not be added to the My contacts list and should display an error message as "Invalid mobile number." . | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: Data is accepted and the option is selected and visible. Step 7: Email address is added and visible. Step 8: Data is accepted. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is added to the My contacts list. | High | P1 | Sunitha Padhi | FAIL | 2023-04-03 | 2023-04-03
TC_007 | US_001 | TS_001 | Add contact tab validation | Validate with blank mobile number | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Do not enter any first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an email address and select any option in the Pick a Label. Step 7: Click on Add email button. Step 8: Do not enter the mobile and work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Kavya Last name: Iyer email: Kavya123@gmail.com mobile no: | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: Data should not be accepted and an error message should be displayed as "The field should not be left blank.". Step 7: The email address should be accepted and visible. Step 8: Should display an error message as "The field should not be left blank." Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: New contact should not be added to the My contacts list and should display an error message as "The field should not be left blank." | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: Data is accepted and the option is selected and visible. Step 7: Email address is added and visible. Step 8: Data is accepted. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is added to the My contacts list. | High | P1 | Sunitha Padhi | FAIL | 2023-04-03 | 2023-04-03
TC_008 | US_001 | TS_001 | Add contact tab validation | Validate with exist mobile number | Step 1: Enter the URL in the browser page. Step 2: Click the CRM button and sign in to your Gmail account. Step 3: Do the mouse hover and click on Add contact button in the My contacts tab. Step 4: Do not enter any first name and last name. Step 5: Select accounts in the dropdown box or add any new account. Step 6: Enter an email address and select any option in the Pick a Label. Step 7: Click on Add email button. Step 8: Enter the mobile number which already exists and enter work details. Step 9: Select the Sales owner in the dropdown box or add any new owner name. Step 10: Select Subscription status, WhatsApp subscription status and SMS subscription status in the respective dropdown boxes. Step 11: Select the Lifecycle stage and the Status dropdown boxes. Step 12: Click on the Save button. | URL = "https://www,freshworks.com" First name: Kavya Last name: Iyer email: Kavya123@gmail.com mobile no:7890000234 | Step 1: Should land on the Freshers Login page. Step 2: Should land on the sales contact page. Step 3: Should be able to select Add contact button and Add contact layover form should be seen on the right side. Step 4: Data should be accepted and visible. Step 5: Options should be seen in the dropdown and should allow adding any new type of account or any other account and the selected account should be accepted and visible. Step 6: Data should not be accepted and an error message should be displayed as "The field should not be left blank.". Step 7: The email address should be accepted and visible. Step 8: Should display an error message as "The mobile number already exists." Step 9: Options should be seen in the dropdown and the selected option should be accepted and visible. Step 10: Options should be seen in the dropdown and selected options should be accepted and visible. Step 11: Options should be seen in the dropdown and selected options should be accepted and visible. Step 12: New contact should not be added to the My contacts list and should display an error message as "The mobile number already exists." | Step 1: Landed on the Freshers Login page. Step 2: Landed on the Sales contact page. Step 3: Add contact button got selected and Add contact layover form is seen on the right side. Step 4: Data is accepted and visible. Step 5: The selected account is accepted and visible. Step 6: Data is accepted and the option is selected and visible. Step 7: Email address is added and visible. Step 8: Data is accepted and visible. Step 9: Options are seen in the dropdown and the selected option is accepted and visible. Step 10: Options are seen in the dropdown and selected options are accepted and visible. Step 11: Options are seen in the dropdown and selected options are accepted and visible. Step 12: New contact is added to the My contacts list. | High | P1 | Sunitha Padhi | FAIL | 2023-04-03 | 2023-04-03
TC-009 | US_001 | TS_001 | Sorting the list | Validate sorting in ascending order with the Name column | Step 1: Click on the dropdown arrow button near the Name column. Step 2: Select the Sort ascending A -> Z option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Name column in ascending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Name column in ascending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_010 | US_001 | TS_001 | Sorting the list | Validate sorting in descending order with the Name column | Step 1: Click on the dropdown arrow button near the Name column. Step 2: Select the Sort descending Z -> A option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Name column in descending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Name column in descending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_011 | US_001 | TS_001 | Sorting the list | Validate sorting in ascending order with the Score column | Step 1: Click on the dropdown arrow button near the Score column. Step 2: Select the Sort ascending 0 -> 9 option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Score column in ascending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Score column in ascending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_012 | US_001 | TS_001 | Sorting the list | Validate sorting in descending order with the Score column | Step 1: Click on the dropdown arrow button near the Score column. Step 2: Select the Sort descending 9 -> 0 option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Score column in descending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Score column in descending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_013 | US_001 | TS_001 | Sorting the list | Validate sorting in Ascending order with Emails column | Step 1: Click on the dropdown arrow button near Emails column. Step 2: Select the Sort Ascending A -> Z option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Emails column in ascending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Emails column in ascending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_014 | US_001 | TS_001 | Sorting the list | Validate sorting in descending order with Emails column | Step 1: Click on the dropdown arrow button near the Emails column. Step 2: Select the Sort descending Z -> A option. | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list should be sorted with respect to the Emails column in descending order. | Step 1: Options are seen in the dropdown and allowed to select the option. Step 2: The Contact list is sorted with respect to the Emails column in descending order. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_015 | US_001 | TS_001 | Editing values at all the fields | Validate the edit icon at all the fields (work field) | Step 1: Click on the right side of Mamta Mohta's work field. Step 2: Enter the value and click on the Save button. | Work value:5444444444 | Step 1: The particular field should be selected and should allow to enter the value. Step 2: The new value should get updated in the field. | Step 1: The particular field is got selected and allowed to enter the value. Step 2: The new value is updated in the field. | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_016 | US_001 | TS_001 | Editing values at all the fields | Validate the edit icon at all the fields (Next activity field) | Step 1: Click on the right side of Spector Calesta's Next activity field. Step 2: Enter the value and click on the Save button. | Task:Auditing | Step 1: The particular field should be selected and should allow to enter the value. Step 2: The new value should get updated in the field. | Step 1: The particular field is got selected and allowed to enter the value. Step 2: The new value is updated in the field. | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_017 | US_001 | TS_001 | Editing values at all the fields | Validate the edit icon at all the fields (Emails field) | Step 1: Click on the right side of Naveen Roy's Emails field. Step 2: Enter the value and click on the Save button. | Email address:naveen123@gmail.com | Step 1: The particular field should be selected and should allow to enter the value. Step 2: The new value should get updated in the field. | Step 1: The particular field is got selected and allowed to enter the value. Step 2: The new value is updated in the field. | High | P1 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_018 | US_001 | TS_001 | Table dropdown Validation | Validate the flow of the Table dropdown | Step 1: Click on the arrow at the right side of the Table dropdown. Step 2: Select any one option(Kanban option). | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list's UI should be updated with respect to the selected option(Kanban). | Step 1: Options are seen in the dropdown and allowed to select the option(Kanban) Step 2: The Contact list's UI is updated with respect to the selected option(Kanban). | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_019 | US_001 | TS_001 | Kanban dropdown Validation | Validate the flow of the Kanban dropdown | Step 1: Click on the arrow at the right side of the Kanban dropdown. Step 2: Select any one option(Table option). | NA | Step 1: Options should be seen in the dropdown and should allow selecting any option. Step 2: The Contact list's UI should be updated with respect to the selected option(Table). | Step 1: Options are seen in the dropdown and allowed to select the option(Kanban) Step 2: The Contact list's UI is updated with respect to the selected option(Table). | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_020 | US_001 | TS_002 | Group by button Validation | Validate to see the options of Group by button | Step 1: Do the mousehover on the Group by button. Step 2: Click on the Group by button. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_021 | US_001 | TS_002 | Group by button Validation | Validate the flow of Group by button | Step 1: Do the mouse hover on the Group by button. Step 2: Click on the Group by button. Step 3: Select the lifecycle stage option in the 'Group your contacts by a field' layover form. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Lifecycle stage value the dashboard should change according to the Lifecycle stage in the form of Kanban. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Lifecycle stage value the dashboard is changed according to the Lifecycle stage value in the form of Kanban. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_022 | US_001 | TS_002 | Group by button Validation | Validate the flow of Group by button | Step 1: Do the mouse hover on the Group by button. Step 2: Click on the Group by button. Step 3: Select the Status option in the 'Group your contacts by a field' layover form. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Status value the dashboard should change according to the Status in the form of Kanban. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Status stage value the dashboard is changed according to the Status value in the form of Kanban. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_023 | US_001 | TS_002 | Group by button Validation | Validate the flow of Group by button | Step 1: Do the mouse hover on the Group by button. Step 2: Click on the Group by button. Step 3: Select the Customer fit option in the 'Group your contacts by a field' layover form. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Customer fit value the dashboard should change according to the Customer fit in the form of Kanban. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the customer fit value the dashboard is changed according to the Customer fit value in the form of Kanban. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_024 | US_001 | TS_002 | Group by button Validation | Validate the flow of Group by button | Step 1: Do the mouse hover on the Group by button. Step 2: Click on the Group by button. Step 3: Select the Customer fit option in the 'Group your contacts by a field' layover form. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Territory value the dashboard should change according to the Territory value in the form of Kanban. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Territory value the dashboard is changed according to the Territory value in the form of Kanban. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03
TC_025 | US_001 | TS_002 | Group by button Validation | Validate the flow of Group by button | Step 1: Do the mouse hover on the Group by button. Step 2: Click on the Group by button. Step 3: Select the Customer fit option in the 'Group your contacts by a field' layover form. | NA | Step 1: The user should able to select the Group by button. Step 2: Options should be seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the none option, the dashboard should change from Kanban to Table form. | Step 1: The user is able to select the Group by button. Step 2: Options are seen in the dropdown of the Group by button and should allow selecting any option. Step 3: On selecting the Territory value the dashboard is changed from Kanban to Table form. | Medium | P2 | Sunitha Padhi | PASS | 2023-04-03 | 2023-04-03

## Test_Execution_Details
Test_Case_No | Test_Case_Name | Snapshots
TC_001 | Add contact tab validation
TC_002 | Add contact tab validation
TC_003 | Add contact tab validation
TC_004 | Add contact tab validation
TC_005 | Add contact tab validation
TC_006 | Add contact tab validation
TC_007 | Add contact tab validation
TC_008 | Add contact tab validation
TC_009 | Sorting the list
TC_010 | Sorting the list
TC_011 | Sorting the list
TC_012 | Sorting the list
TC_013 | Sorting the list
TC_014 | Sorting the list
TC_015 | Editing values at all the fields
TC_016 | Editing values at all the fields
TC_017 | Editing values at all the fields
TC_018 | Table dropdown Validation
TC_019 | Kanban dropdown Validation
TC_020 | Group by button Validation
TC_021 | Group by button Validation
TC_022 | Group by button Validation
TC_023 | Group by button Validation
TC_024 | Group by button Validation
TC_025 | Group by button Validation
TC_026
TC_027
TC_028
TC_029
TC_030
TC_031
TC_032
TC_033
TC_034
TC_035
TC_036
TC_037
TC_038
TC_039
TC_040
TC_041
TC_042
TC_043
TC_044
TC_045
TC_046
TC_047
TC_048
TC_049
TC_050
TC_051
TC_052
TC_053
TC_054
TC_055
TC_056

## Defects
Defect_No | Project Name | Module Name | Requirement_No | Test_Case_No | Summary | Descriptiom | Issues | Severity | Priority | Assign to | Screenshots
DN_001 | CRM Freshworks | CRM Contacts | User_Story_001 | TC_005 | Validate Add contact tab | When the user left the first name and last name blank and clicks on the Save button, the contact gets added to the list. But it should display an error message as "The field should not be left blank.". | The contact gets added up to the list without first name and last name. | High | P1 | Sunitha Padhi
DN_002 | CRM Freshworks | CRM Contacts | User_Story_001 | TC_006 | Validate Add contact tab | When the user enters an invalid number and clicks on the Save button, the contact gets added to the list. But it should display an error message as "Invalid mobile number.". | The contact gets added up to the list with invalid mobile number. | High | P1 | Sunitha Padhi
DN_003 | CRM Freshworks | CRM Contacts | User_Story_001 | TC_007 | Validate Add contact tab | When the user left the mobile number blank and clicks on the Save button, the contact gets added to the list. But it should display an error message as "The field should not be left blank.". | The contact gets added up to the list without mobile number. | High | P1 | Sunitha Padhi
DN_004 | CRM Freshworks | CRM Contacts | User_Story_001 | TC_008 | Validate Add contact tab | When the user enters the mobile number which already exists and clicks on the Save button, the contact gets added to the list. But it should display an error message as "The mobile number already exists.". | The contact gets added up to the list with the mobile number which already exists. | High | P1 | Sunitha Padhi

## Test_Report
SNO | PASS | FAIL | BLOCKERS | NOT EXECUTED | TOTAL TEST CASE | PASS RATIO(%) | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT